## Original Plan
Yearly Plan 2023
Quarterly Q2
Build CI/CD pipeline |  | Start Date | End Date
Week (Estimation of time) |  |  | Sprint | Release # | Task | Subtask | Status
Week 1 | 25/06/2023 | 27/06/2023 | Sprint 1 |  | Overview | Overview requirements | TODO
| 25/06/2023 | 27/06/2023 |  |  |  | Estimate | TODO
| 27/06/2023 | 28/06/2023 |  |  | CI: Set Up Azure Cloud Shell | Create the Cloud-Based Development Environment | TODO
| 27/06/2023 | 28/06/2023 |  |  |  | Create Project Scaffolding | TODO
| 27/06/2024 | 28/06/2023 |  |  |  | Local Test | TODO
| 29/06/2023 | 30/06/2023 | Sprint 2 | 0.1 | Deploy to wepapp | Run local test | TODO
Week 2 | 29/06/2023 | 30/06/2023 |  |  |  | Create resource group | TODO
| 29/06/2023 | 30/06/2023 |  |  |  | Create web app | TODO
| 30/06/2023 | 2023-07-04 |  |  |  | Deploy to webapp | TODO
| 30/06/2023 | 2023-07-04 |  | 0.2 | CI: Configure GitHub Actions | Enable Github Actions | TODO
| 30/06/2023 | 2023-07-04 |  |  |  | Update YML code | TODO
| 30/06/2023 | 2023-07-04 |  |  |  | Verify Remote Tests pass | TODO
Week 3 | 2023-07-05 | 2023-07-08 | Sprint 3 | 0.3 | Continuous Delivery on Azure | Get Flask Starter Code | TODO
| 2023-07-05 | 2023-07-08 |  |  |  | Replace scaffolding code with Flask Starter Code | TODO
| 2023-07-05 | 2023-07-08 |  |  |  | Authorize Azure App Service | TODO
| 2023-07-05 | 2023-07-08 |  |  |  | Checkin Azure Pipelines YAML based congig into Github | TODO
| 2023-07-05 | 2023-07-08 |  |  |  | Create Agent Pool | TODO
| 2023-07-09 | 2023-07-11 |  |  |  | Create VM agent | TODO
| 2023-07-09 | 2023-07-11 |  |  |  | Test deployed | TODO
| 2023-07-09 | 2023-07-11 | Sprint 4 | 1 | Prepare for submit project | Take screenshot | TODO
Week 4 | 2023-07-09 | 2023-07-11 |  |  |  | Update readme | TODO
| 2023-07-12 | 2023-07-14 |  |  |  | Create demo and upload to Youtube | TODO
| 2023-07-12 | 2023-07-14 |  |  | Submit project | Submit project | TODO
| 2023-07-12 | 2023-07-14 |  |  |  | Waiting for review | TODO
| 2023-07-12 | 2023-07-14 |  |  | Clean up project |  | TODO
Top 3 Quarter Goal |  | Order | Proposed Disfficulty 1-3 |  |  | Goals | Project management guidelines
Uderstand the deliverables |  |  | 1 |  |  |  | Daily meeting
Code is ready for CI/CD |  |  | 1 |  |  |  | Internal demo in last week
Documentation |  |  | 2

## Actual Plan
Yearly Plan 2023
Quarterly Q2
Build CI/CD pipeline |  | Start Date | End Date
Week (Estimation of time) |  |  | Sprint | Release # | Task | Subtask | Status
Week 1 | 25/06/2023 | 27/06/2023 | Sprint 1 |  | Overview | Overview requirements | Done
| 25/06/2023 | 27/06/2023 |  |  |  | Estimate | Done
| 27/06/2023 | 28/06/2023 |  |  | CI: Set Up Azure Cloud Shell | Create the Cloud-Based Development Environment | Done
| 27/06/2023 | 28/06/2023 |  |  |  | Create Project Scaffolding | Done
| 27/06/2024 | 28/06/2023 |  |  |  | Local Test | Done
| 29/06/2023 | 30/06/2023 | Sprint 2 | 0.1 | Deploy to wepapp | Run local test | Done
Week 2 | 29/06/2023 | 30/06/2023 |  |  |  | Create resource group | Done
| 29/06/2023 | 30/06/2023 |  |  |  | Create web app | Done
| 30/06/2023 | 2023-07-04 |  |  |  | Deploy to webapp | Done
| 30/06/2023 | 2023-07-04 |  | 0.2 | CI: Configure GitHub Actions | Enable Github Actions | Done
| 30/06/2023 | 2023-07-04 |  |  |  | Update YML code | Done
| 30/06/2023 | 2023-07-04 |  |  |  | Verify Remote Tests pass | Done
Week 3 | 2023-07-05 | 2023-07-08 | Sprint 3 | 0.3 | Continuous Delivery on Azure | Get Flask Starter Code | Done
| 2023-07-05 | 2023-07-08 |  |  |  | Replace scaffolding code with Flask Starter Code | Done
| 2023-07-05 | 2023-07-08 |  |  |  | Authorize Azure App Service | Done
| 2023-07-05 | 2023-07-08 |  |  |  | Checkin Azure Pipelines YAML based congig into Github | Done
| 2023-07-05 | 2023-07-08 |  |  |  | Create Agent Pool | Done
| 2023-07-09 | 2023-07-11 |  |  |  | Create VM agent | Done
| 2023-07-09 | 2023-07-11 |  |  |  | Test deployed | Done
| 2023-07-09 | 2023-07-11 | Sprint 4 | 1 | Prepare for submit project | Take screenshot | Done
Week 4 | 2023-07-09 | 2023-07-11 |  |  |  | Update readme | Done
| 2023-07-12 | 2023-07-14 |  |  |  | Create demo and upload to Youtube | In progess
| 2023-07-12 | 2023-07-14 |  |  | Submit project | Submit project | In progess
| 2023-07-12 | 2023-07-14 |  |  |  | Waiting for review | In progess
| 2023-07-12 | 2023-07-14 |  |  | Clean up project |  | TODO
Top 3 Quarter Goal |  | Order | Proposed Disfficulty 1-3 |  |  | Goals | Project management guidelines
Uderstand the deliverables |  |  | 1 |  |  |  | Daily meeting
Code is ready for CI/CD |  |  | 2 |  |  |  | Internal demo in last week
Documentation |  |  | 2 |  |  |  | Teamwork

## Yearly Plan
Year | Goal
2023 | Implement and upgrade project
2024 | Improve skill and get certificate
2025 | Applied for DevOps engineer